## REMEDIATION EXECUTION
ENVIRONMENTAL REMEDIATION UNIT
PROJECT TITTLE: PHASE 2 REMEDIATION OF HYDROCARBON IMPACTED SITE
SCOPE OF WORK: To carryout the remediation of hydrocarbon soil and groundwater in 39 Simple Medium Risk sites.
DURATION: 2 YEARS
STATUS OF WORKS
S/N | Lot No. | Site Name | Contractors Name | Status of Work | Overall work completion Percentage (%)
1 | SMR 001 | Ajeokpori-1, Ogale, Eleme LGA | Beachstone Limited | 1. Site office setup completed | 7.5
2. Completed site assessment/Characterization field sampling and data collection.
3. Submitted Site characterization report and Remediation Action Plan
4. Biocell Construction ongoing
2 | SMR 002 | Ajeokpori-2, Ogale, Eleme LGA | Avondale Services and Supplies Limited | 1. Completed site assessment/Characterization field sampling and data collection. | 9.5
2. Submitted Site Characterization Report and Remediation Action Plan
3. Completed Office setup
4. Biocell construction ongoing
3 | SMR 003 | Ajeokpori-3, Ogale, Eleme LGA | Earthpro Unique Integrated Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 8
2. Submitted Site characterization report RAP.
3. Completed Office setup
4 | SMR 004 | Ajeokpori-4, Ogale, Eleme LGA | Newline West Africa Limited | 1. Completed site assessment/Characterization field sampling and data collection. | 14.5
2. Completed Office setup
3. Submitted site characterization report
4. Remediation Action ongoing: Excavation of impacted soils in trenches and Installation of injection wells for biosparging around the trenches
5 | SMR 005 | Site A: Ajeokpori-5, Ogale, Eleme LGA | Ecosafe Services Ltd | 1. Site Office Setup completed | 8.5
|  | Site B : |  | 2. Site assessment/characterization field sampling and data collection completed
|  | Okuluebu, Ogale, Eleme LGA |  | 3. Biocell Construction ongoing
6 | SMR 006 | Ajeokpori-6, Ogale, Eleme LGA | Icren Services Limited | 1. Completed site assessment/Characterization field sampling and data collection. | 9.5
2. Submitted site characterization report and RAP.
3. Completed Site Office Setup
4. Biocell Construction ongoing
7 | SMR 007 | Ajeokpori-7, Ogale, Eleme LGA | Geokooy Environmental Services Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 9
2. Development of site characterization report ongoing.
3. Site Office setup completed
4. Biocell Construction ongoing
8 | SMR 008 | Ajeokpori-8, Ogale, Eleme LGA | Cagewox Dot Net Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 9
2. Preparation of site characterization report ongoing.
3. Site Office setup completed
4. Biocell Construction ongoing
9 | SMR 009 | Ajeokpori-9, Ogale, Eleme LGA | Foxtrot O&G Company Nigeria Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 9
2. Developing site characterization report and RAP.
3. Site Office setup completed
4. Biocell Construction ongoing -
10 | SMR 010 | Ajeokpori-10, Ogale, Eleme LGA | Lamor Corp Ab & Dinetuks Nigeria Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 7
2. Submitted Site Characterization report and RAP.
3. Completed Site Office setup
11 | SMR 011 | Ajeokpori-11, Ogale, Eleme LGA | Stefanutti Stocks Hapel Ltd | 1. Completed Site assessment/Characterization field sampling and data collection | 7
2. Submitted site characterization report and RAP
3. Site Office Setup ongoing
12 | SMR 012 | Ajeokpori-12, Ogale, Eleme LGA | Fibow Petroleum Environmental Engineering Consult Ltd | 1. Site Office setup completed | 5.5
2. Completed Site characterization field sampling and data collection
13 | SMR 013 | Ajeokpori-13, Ogale, Eleme LGA | Nopec Energy Services Ltd | 1. Completed site Office Setup | 9
2. Completed Site assessment/Characterization field sampling and data collection
3. Biocell Construction ongoing
14 | SMR 014 | Ogale-Ogale, Ogale, Eleme LGA | One Specialty P & S Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 12.5
2. Submitted and Approved site characterization report and RAP.
3. Site Office setup Completed
4. Commenced Remediation Works: Excavation of impacted Trenches.
15 | SMR 015 | Obaji Oken, Ogale Eleme LGA | Giolee Global Resources Limited | 1. Completed site assessment/Characterization field sampling and data collection. | 16.5
2. Submitted and Approved site characterization report and RAP
3. Completed Office setup
4. Biocell Construction completed
5. The ongoing remediation phase: commenced Biosparging using constructed injection wells and excavating trenches of impacted soils.
16 | SMR 016 | Omunwanwan, Sime, Tai LGA | Vitruvian Global Resources Limited | 1. Completed site assessment/Characterization field sampling and data collection. | 10
2. Submitted Site characterization report and RAP
3. Site Office setup completed
4. Biocell Construction ongoing
17 | SMR 016B | Barabeedom, K-Dere, Gokana | Esinos Resources International Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 6
2. Development of Site characterization report ongoing.
3. Office Setup Ongoing
4. Biocell Construction ongoing
18 | SMR 017 | Omunwanwan, Sime, Tai LGA | Craneburg Construction Company Ltd | 1. Completed Site assessment/Characterization field sampling and data collection | 8
2. Site office setup ongoing
3. Development of Site characterization report ongoing.
4. Biocell Construction Ongoing
19 | SMR 018 | Wiikayako (Well 10), Kpean, Khana LGA | Katech Construction Co. Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 10.5
2. Development of Site characterization report ongoing.
3. Completed Site Office setup
4. Biocell Construction ongoing
20 | SMR 019 | Muuborgbara, Biara, Gokana LGA | Jezreel Engineering Services Limited | 1. Completed Site assessment/Characterization field sampling and data collection | 6
2. Office setup ongoing
21 | SMR 020 | Bara Yiema, Kpite, Tai LGA | Welltime Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 11
2. Submitted Site characterization report and RAP
3. Completed Office setup
4. Biocell construction ongoing
22 | SMR 020B | Barabeedom, K-Dere, Gokana | Chayoobi Nig Ltd | 1. Completed Site Characterization and assessment field sampling. | 8.5
2. Submitted Site characterization report and RAP
3. Site office setup ongoing
23 | SMR 021 | Biara, Biara, Gokana LGA | Satel Construction Nig. Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 9.5
2. Submitted Site characterization report and RAP
3. Completed Site office setup
4. Biocell Construction ongoing
24 | SMR 022 | Bera-Bera P/L1, Bera, Gokana LGA | Duluidas Nig. Ltd | 1. Completed Site Assessment and characterization field sampling. | 6.5
2. Developing site characterization Report and RAP
25 | SMR 023 | Bera P/L1-3, Bera, Gokana LGA | Acti & Air Power | 1. Completed Site Assessment and characterization Field Sampling and Data collection. | 5.5
2. Developing site characterization Report and RAP
26 | SMR 024 | Bera P/L1-3, Bera, Gokana LGA | Roxcon Nigeria Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 7.5
2. Submitted Site characterization report and RAP
3. Site setup (Clearing of site areas and Office setup) ongoing
27 | SMR 025 | Bera P/L1-3, Bera, Gokana LGA | Barewa Investment Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 10.5
2. Submitted Site Characterization Report and RAP.
3. Site Office setup ongoing
4. Biocell Construction ongoing
28 | SMR 026 | Boobanabe PL 1-2, K-Dere, Gokana LGA | Karidav Integrated Services Ltd | 1. Completed Site Assessment/Characterization field sampling/data collection | 8
2. Submitted site characterization Report
3. Site Office setup completed
29 | SMR 027 | Boobanabe PL 1-2, K-Dere, Gokana LGA | Transcend Construction Ltd | 1. Completed Site Assessment/Characterization field sampling/data collection | 10
2. Site Office setup Completed
3. Submitted site characterization Report and RAP
4. Biocell Construction ongoing
30 | SMR 028 | Gior, K-Dere, Gokana LGA | Toledo Engineering Ltd | 1. Contractor yet to mobilize to site | 2.5
31 | SMR 029 | Gior, K-Dere, Gokana LGA | Bussdor & Comp Ltd | 1. Contractor yet to mobilize to site | 2.5
32 | SMR 030 | Kegbara Kpor, Kpor, Gokana LGA | Thaworld Global Resources Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 11
2. Submitted Site characterization report and RAP.
3. Completed Site Office setup
4. Biocell Construction ongoing
33 | SMR 031 | Debon, Mogho-Bodo, Gokana LGA | Telmac Engineering Ltd | 1. Contractor Yet to mobilize to site | 0.5
34 | SMR 032 | Peeteh / Boobanabe, K-Dere, Gokana LGA | Halliday Global Services | 1. Completed Site Assessment/Characterization field sampling/data collection. | 8
2. Developing site characterization Report and RAP
3. Construction of Engineered Biocell ongoing
4. Site office setup ongoing
35 | SMR 033 | Peeteh / Boobanabe, K-Dere, Gokana LGA | Lapideo Multi Services Ltd | 1. Completed Site Assessment/characterization field sampling | 7
2. Submitted Site Characterization Report and RAP
3. Site office setup ongoing
36 | SMR 034 | Peeteh / Boobanabe, K-Dere, Gokana LGA | ZGM Investment Group of Companies Ltd | 1. Site characterization field sampling ongoing | 4.5
37 | SMR 035 | Kwawa Flow Station & Flare Site, Kwawa, Khana LGA | Engineering Seven Integrated Konsult Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 10
2. Office setup completed.
3. Biocell Construction
38 | SMR 036 | Kwawa Flow Station & Flare Site, Kwawa, Khana LGA | Philcom Integrated Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 13.5
2. Submitted Site characterization report and RAP
3. Office setup completed
4. Biocell Construction completed
5. Commenced Remediation Phase: Excavation of impacted soils in trenches and transfer of soils into biocell
39 | SMR 037 | Wiikayako (Well 10), Kpean, Khana LGA | Shearforce Nig Ltd | 1. Completed site assessment/Characterization field sampling and data collection. | 11.5
2. Submitted Site characterization Report and RAP.
3. Office setup completed
4. Biocell Construction ongoing
| Overall Percentage Completion |  |  |  | 8.47

## ENVIRONMENTAL SITE ASSESSMENT
ENVIRONMENTAL REMEDIATION UNIT
PROJECT TITTLE: RAPID SITE CHARACTERIZATION
SCOPE OF WORK: To carryout the characterization and scope verification of 39 Simple Medium Risk sites to have a regional baseline of contamination on Site
DURATION: 3 MONTHS
STATUS OF WORKS
S/N | Cluster | Lots in Cluster | Site Name | Contractors/Consultant/Responsible Party | Status of Work | Overall work completion Percentage (%)
1 | Cluster 1 | Lots 1 – 8 | Ajeokpori, Ogale, Eleme LGA | Rivers State University, Nkporlu, Port Harcourt. | 1. Site/Field Work completed | 95
2. Final Report submitted
3. Final Report Review Ongoing
2 | Cluster 2 | Lots 9 - 17 | 1. Ajeokpori, Ogale, Eleme. 2. Obaji Oken, Ogale Eleme. 3. Omunwanwa, Sime | Groundscan Nigeria Limited | 1. Site/Field Work completed | 95
2. Final Report submitted
3. Final Report Review Ongoing
3 | Cluster 3 | Lot 18 Lots 22 - 27 Lots 32 -37 | 1. Bera, Bera Gokana 2. Boobanabe, K-Dere Gokana 3. Wiikayako, Kpean, Khana 4. Flow Station, Kwawa Khana | University of Port Harcourt | 1. Four (4) out of Thirteen (13) Lots done however, GPR is yet to commence. | 35
2. Work yet commence on Nine (9) out of Thirteen (13) Lots
4 | Cluster 4 | Lots 16B Lots 19 - 21 Lots 28 - 31 | 1. Muuborgbara/Boobaamuu, in Biara - Gokana 2. Barayiemaa in Kpite - Tai 3. Barabeedom in K-Dere - Gokana 4. Kpor, Kpor in Gokana 5. Gior in Kpor, Mogho & K-Dere 6. Debon in Mogho/Bodo) | Geoterrain Nigeria Limited | 1. Site/Field Work completed | 90
2. Final Report submitted
3. Yet to submit Final Report
PROJECT TITTLE: DETAILED SITE ASSESSMENT AND DELINEATION SAMPLING
SCOPE OF WORK: To carryout Detailed Site Assessment/Delineation of Simple to Medium Risk Sites
DURATION: 1 WEEK
STATUS OF WORKS
5 | N/A | N/A | Okuluebu 1, Ogale, Eleme | HYPREP | 1. Hand Auger done. 2. Cable Percussion Drilling done. 3. Maps and Delineation done | 100
6 | N/A | N/A | Yola, Kwawa, Khana | HYPREP | 1. Hand Auger done. 2. Cable Percussion Drilling done. 3. Maps and Delineation done | 100
7 | N/A | N/A | Orsaakani, Kira, Tai | HYPREP | 1. Hand Auger done. 2. Cable Percussion Drilling done. 3. Maps and Delineation done | 100

## QAQC
ENVIRONMENTAL REMEDIATION UNIT (QAQC SUB UNIT)
PROJECT TITTLE: PHASE 2 REMEDIATION OF HYDROCARBON IMPACTED SITE, SHORELINE CLEANUP & SITE ASSESSMENT
SCOPE OF WORK: To verify the remediation of hydrocarbon impacted soil and groundwater in 39 Simple Medium Risk sites, Verify Shoreline cleanup and Site Assessment
TEAM | ACTIVITY | STATUS OF WORK DONE | DURATION/TIME LINE | CONTRACTORS DETAILS | LOOK AHEADS | REMARKS
QUALITY ASSURANCE & QUALITY CONTROL | CLOSE OUT | CLOSED OUT SAMPLING DONE IN LOT 32 B.DERE GOKANA, RESAMPLING IN LOT 11 DEBON-MOGHO/BODO , LOT 23 B.DERE, LOT 31 B.DERE, | JANUARY AND FEBRUARY 2024 | LOT 11-MOSVINY, LOT 23- CASCADE, LOT 31-OILSERVE, LOPT 32 MOSITO | CLOSE OUT OF OKULUEBU BY DECEMBER 2024 | 95% COMPLETED
| VERIFICATION SAMPLING | ONGOING, HAD DONE 2 ROUNDS OF SAMPLING, ONCE IN JANUARY AND ONCE IN FEBUARY 2024 | 24 MONTHS | GIOLEE GLOBAL RESOURCES | 10 ROUNDS OF VERIFICATION SAMPLING BY DECEMBER 2024 | 10%
|  | ONGOING AT LOT 4. ONCE FERBRUARY 2024 | 24 MONTHS | WELL TIME | 10 ROUNDS OF VERIFICATION SAMPLING BY DECEMBER 2024 | 3%
| SITE CHARACTERIZATION SAMPLING | COMPLETED IN 33 LOTS | 6 MONTHS | SMR LOT1-15 IN ELEME, LOT 16, 17 AND 20 IN TAI, LOT 16B LOT 19, 20B, 21-27,30 IN GOKANA, 18, 35-37 IN KHANA | COMPLETION OF ALL SITE CHARACTERIZATION IN ALL THE REMAING 4 LOTS | 80% COMPLETED
|  | ONGOING IN LOT 34 |  | ONGOING IN LOT 34 | COMMENCEMENT AND COMPLETION OF SITE CHARACTERIZATION IN LOT 28, 29, 31 AND 32
| VALUATION OF WORK DONE | DONE IN SMR LOT 002, LOT 003, LOT 004, LOT 015, LOT 16 | 24 MONTHS | DONE IN SMR LOT 002, LOT 003, LOT 004, LOT 015, LOT 16 | VALUATION IN ALL 30 SMR LOTS BY DECEMBER 2024 | 10%
| RAPID SCAT SURVEY 2 @ BOMU | COMPLETED | JANEUARY AND FEBRUARY 2024 | 34 REMEDIATION LOTS IN GOKANA | COMPLETED | 100%
| PRE-SCAT SURVEY | ONGOING, COMPLETED IN TAI, GOKANA AND KHANA | 12 MONTHS | ONGOING, COMPLETED IN TAI, GOKANA AND KHANA | ASSESS 15 DISCOVERED ARTISANAL SITES | 10%
| VERIFICATION SAMPLING IN SHORELINE AFTER FLUSHING | YET TO START | 36 MONTHS | TO CARRY OUT VERIFICATION SAMPLING IN SHORELINE, GRID BY GRID AFTER FLUSHING | TO CARRY OUT VERIFICATION SAMPLING IN SHORELINE, GRID BY GRID AFTER FLUSHING | 0%
| BASELINE SAMPLING AT BASE CAMP AND TEMPORARY STORAGE AREA | WILL START IN FEBRUARY 2023 | 4 MONTHS | YET TO START | BASELINE SAMPLING OF ALL 34 SHORELINE REMEDIATION BASE CAMP AND TEMPORARY STORAGE AREA | 0%
| SAMPLING OF IMPACTED SITES | COMPLETED IN KWAWA MANIFOLD | 12 MONTHS |  | SAMPLING OF 10 IMPACTED SITES | 10%

## MRP
MANGROVE RESTORATION PROJECT CONTRACTORS WORK STATUS REPORT
PROJECT TITLE: Phase 1 Planting of Mangrove seedlings on non-contaminated Shoreline areas(592.63 hectares)
SCOPE OF WORK: To undertake revegetation of Clean-up Mangrove Vegetation area.
LOT NO | CONTRACTOR | ACTIVITY | TASK DESCRIPTION | STATUS(% of Premobilization stage) | LOOK AHEAD
MRP 001 | Panda Giant Developer Ltd | 1.Premobilization Activities. 2. Community enetering payments. | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment 3. Payment of Compensation for Base camp area | 90 | 1. Completion of medical fitness and swim test. 2.Mangrove transplanting training. 3.Base Camp Clearing. 4.Sourcing of Mangrove seedlings/propagules. 5. Transplanting activity
MRP 002 | 2C's Project Limited |  | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment . | 80
MRP 003 | Fabseg Resources Limited |  | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment. | 80
MRP 004 | Basic Nigeria Technology Limited |  | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment. 3. Payment of Compensation for Base camp area | 90
MRP 005 | A&T HDPE Liner Containment Ltd |  | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment. | 80
MRP 006 | Goldstream Investment Limited |  | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment. 3. Payment of Compensation for Base camp area | 90
MRP 007 | Nielson Nigeria Limited |  | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment. 3. Payment of Compensation for Base camp area | 90
MRP 008 | Tedcorp Limited |  | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment. | 80
MRP 009 | Abduganas Limited |  | 1.Medical fitness screening, Swim test, IMO training. 2. Homage payment. | 80